## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
S1 | S1 | US-001 | Introduction to the project (AI powered Regulatory Compliance Ckecker for Contracts) | WON'T HAVE | No Dependency | Aditya Goswami | 3- Completed
S1 | S1 | US-001 | Set up the environment for data collection and Training for using LLM's for contract analysis | COULD HAVE | Libraries and Frameworks | Aditya Goswami | 3- Completed
S1 | S1 | US-001 | Collection of initial data from contract documents | MUST HAVE | Data and LLM's | Aditya Goswami | 3- Completed
S2 | S2 | US-001 | Clause Identification and Risk Analysis Engine | MUST HAVE | LLM's, NLP models | Aditya Goswami | 3- Completed
S2 | S2 | US-001 | Implement LLM's to extract key clauses and Build a risk assessment algorithm | MUST HAVE | LLM's, NLP models | Aditya Goswami | 3- Completed
S3 | S3 | US-001 | Regualtory Update Tracking System and Contract Modification Module | MUST HAVE | LLM's, NLP models | Aditya Goswami | 3- Completed
S3 | S3 | US-001 | Integrate API's that track legal changes | MUST HAVE | LLM's, NLP models | Aditya Goswami | 3- Completed
S3 | S3 | US-001 | Build a system that automatically applies relevant updates to active contracts | MUST HAVE | LLM's, NLP models | Aditya Goswami | 3- Completed
S3 | S3 | US-001 | Implement a system that suggests amendments to contracts | MUST HAVE | LLM's, NLP models | Aditya Goswami | 3- Completed
S4 | S4 | US-001 | Multi-platform Integration and Notification System Deployment | MUST HAVE | Google Sheets | Aditya Goswami | 3- Completed
S4 | S4 | US-001 | Integrate the system for real time alerts and Test the notification system by sending alerts | MUST HAVE | Google Sheets | Aditya Goswami | 3- Completed
Note on F1: ====== ID#AAABusQhIM8 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
US-001 | 1 | Introduction to the project (AI powered Regulatory Compliance Ckecker for Contracts) | 2025-09-30 | 2025-10-01 | Aditya Jagadish Manasa | Build | 3- Completed
US-001 | 2 | Set up the environment for data collection and Training for using LLM's for contract analysis | 2025-10-02 | 2025-10-03 | Aditya Jagadish Manasa | Design | 3- Completed
US-001 | 3 | Collection of initial data from contract documents | 2025-10-06 | 2025-10-10 | Aditya Jagadish Manasa | Coding | 3- Completed
US-001 | 4 | Clause Identification and Risk Analysis Engine | 2025-10-13 | 2025-10-17 | Aditya Jagadish Manasa | Coding | 3- Completed
US-001 | 5 | Implement LLM's to extract key clauses and Build a risk assessment algorithm | 2025-10-23 | 2025-10-25 | Aditya Jagadish Manasa | Coding | 3- Completed
US-001 | 6 | Regualtory Update Tracking System and Contract Modification Module | 2025-10-27 | 2025-10-30 | Aditya Jagadish Manasa | Integration Test | 3- Completed
US-001 | 7 | Integrate API's that track legal changes | 2025-10-31 | 2025-11-01 | Aditya Jagadish Manasa | Integration Test | 3- Completed
US-001 | 8 | Build a system that automatically applies relevant updates to active contracts | 2025-11-03 | 2025-10-06 | Aditya Jagadish Manasa | Unit Test | 3- Completed
US-001 | 9 | Implement a system that suggests amendments to contracts | 2025-10-06 | 2025-10-08 | Aditya Jagadish Manasa | Unit Test | 3- Completed
US-001 | 10 | Multi-platform Integration and Notification System Deployment | 2025-11-10 | 2025-11-11 | Aditya Jagadish Manasa | System Test | 3- Completed
US-001 | 11 | Integrate the system for real time alerts and Test the notification system by sending alerts | 2025-11-12 | 2025-11-14 | Aditya Jagadish Manasa | System Test | 3- Completed
Note on D2: ====== ID#AAABusQhINw Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on E2: ====== ID#AAABusQhINU Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on I3: ====== ID#AAABusQhINg Sumeet Kumar Barua08 (2025-01-27 09:44:41) This is the total task estimated in hours for all the user stories
Note on J3: ====== ID#AAABusQhINk Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 1 work
Note on K3: ====== ID#AAABusQhIM0 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 2 work
Note on L3: ====== ID#AAABusQhINc Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 3 work
Note on M3: ====== ID#AAABusQhIM4 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 4 work
Note on N3: ====== ID#AAABusQhINI Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 5 work
Note on O3: ====== ID#AAABusQhIN0 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 6 work
Note on P3: ====== ID#AAABusQhIN4 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 7 work
Note on Q3: ====== ID#AAABusQhINM Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 8 work
Note on R3: ====== ID#AAABusQhINA Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 9 work
Note on S3: ====== ID#AAABusQhINQ Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 10 work
Note on T3: ====== ID#AAABusQhINo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 11 work
Note on U3: ====== ID#AAABusQhINs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 12 work
Note on V3: ====== ID#AAABusQhINE Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 13 work
Note on W3: ====== ID#AAABusQhINY Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
S1 | Day 3 | To set up the environment for data collection and Training for using LLM's for contract analysis | Conducted a detailed discussion with mentors and team
S2 | Day 25 | To implement LLM's to extract key clauses and Build a risk assessment algorithm | Conducted a detailed discussion with mentors and team
S3 | Day 35 | To build a system that automatically applies relevant updates to active contracts | Conducted a detailed discussion with the team
S4 | Day 50 | To integrate the system for real time alerts and Test the notification system by sending alerts | Conducted a detailed discussion with the team

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | S1 | 29/09/2025 | 2025-10-10 | Aditya, Jagadish, Manasa | Reviewing documentation regularly | Assuming project requirements are clear | Participating in discussions and meetings | Scheduled a review session with team and mentors to clarify project goals.
2 | S2 | 13/10/2025 | 25/10/2025 | Aditya, Jagadish, Manasa | Prioritizing Python practice | Delaying review of tasks | Maintaining focus on coding | Achieved Python kit completion on time
3 | S3 | 27/10/2025 | 2025-08-11 | Aditya, Jagadish, Manasa | Preparing SQL practice | Rushing through SQL concepts. | Asking for help when stuck. | Completed SQL with support from the team
4 | S4 | 2025-10-11 | 14/11/2025 | Aditya, Jagadish, Manasa | Participating in Module 1 discussions | Delaying voice input exploration | Collaborating on language processing strategies | Completed voice input prototypes and received team feedback for improvements.